## Engagement Checklist
RMF ENGAGEMENT CHECKLIST — Program Milestone Alignment
Use this checklist to ensure all RMF stakeholders are engaged at the correct program milestone. Attach completed checklist to eMASS package.
Milestone / Phase | RMF Step | Required Action | Lead Role | Supporting Roles | Due Date | Status
Concept/Pre-Milestone A | Step 1 – Categorize | Identify system owner and assign ISSO/ISSM billets | PM | ISSM, ISSE |  | ☐ Not Started
Concept/Pre-Milestone A | Step 1 – Categorize | Conduct initial mission impact analysis; draft system boundary | ISSE | PM, ISSM |  | ☐ Not Started
Concept/Pre-Milestone A | Step 1 – Categorize | Complete FIPS 199 categorization (C/I/A levels) | ISSM | ISSE, SO |  | ☐ Not Started
Concept/Pre-Milestone A | Step 1 – Categorize | Register system in eMASS; assign eMASS roles | ISSM | PM, ISSO |  | ☐ Not Started
Milestone A – Program Initiation | Step 2 – Select Controls | Select initial control baseline (Low/Mod/High) in eMASS | ISSM | ISSE |  | ☐ Not Started
Milestone A – Program Initiation | Step 2 – Select Controls | Apply organization-defined overlays and tailoring | ISSM | ISSE, AO Rep |  | ☐ Not Started
Milestone A – Program Initiation | Step 2 – Select Controls | Hold SSE Kickoff — brief all stakeholders on RMF obligations | PM | ISSM, ISSO, ISSE, AO Rep |  | ☐ Not Started
Milestone A – Program Initiation | Step 2 – Select Controls | Draft System Security Plan (SSP) outline in eMASS | ISSM | ISSO, ISSE |  | ☐ Not Started
SDD / Design Phase | Step 3 – Implement Controls | Integrate security controls into system design (SSE participation) | ISSE | System Engineer, ISSO |  | ☐ Not Started
SDD / Design Phase | Step 3 – Implement Controls | Document control implementation statements in eMASS SSP | ISSO | ISSE |  | ☐ Not Started
SDD / Design Phase | Step 3 – Implement Controls | Upload supporting artifacts; link to controls in eMASS | ISSO | ISSM |  | ☐ Not Started
SDD / Design Phase | Step 3 – Implement Controls | Identify residual risks; open draft POA&Ms for known gaps | ISSM | ISSO, PM |  | ☐ Not Started
Pre-Test / CDR | Step 4 – Assess Controls | Finalize Security Assessment Plan (SAP); lock scope | SCA / Assessor | ISSM, ISSO |  | ☐ Not Started
Pre-Test / CDR | Step 4 – Assess Controls | Run STIG/SCAP scans; document results in eMASS | ISSO | ISSE, SCA |  | ☐ Not Started
Pre-Test / CDR | Step 4 – Assess Controls | Conduct Technical Review Evaluation (TRE) | SCA / Assessor | ISSM, ISSO |  | ☐ Not Started
Pre-Test / CDR | Step 4 – Assess Controls | Adjudicate findings; update POA&Ms with root causes and milestones | ISSM | ISSO, PM |  | ☐ Not Started
IOT&E / System Integration | Step 4 – Assess Controls | Complete Security Assessment Report (SAR) | SCA / Assessor | ISSM |  | ☐ Not Started
IOT&E / System Integration | Step 5 – Authorize | Compile authorization package: SSP, SAR, POA&M, RMF checklist | ISSM | ISSO, PM |  | ☐ Not Started
IOT&E / System Integration | Step 5 – Authorize | PM review and endorsement of authorization package | PM | ISSM |  | ☐ Not Started
IOT&E / System Integration | Step 5 – Authorize | Submit package to AO for review | ISSM | PM, SCA |  | ☐ Not Started
ATO Decision | Step 5 – Authorize | AO issues ATO, IATO, or DATO with conditions | AO | ISSM, PM |  | ☐ Not Started
Post-ATO / O&M | Step 6 – Monitor | Establish continuous monitoring strategy; schedule scans | ISSM | ISSO |  | ☐ Not Started
Post-ATO / O&M | Step 6 – Monitor | Execute monthly/quarterly STIG scans; update eMASS | ISSO | ISSM |  | ☐ Not Started
Post-ATO / O&M | Step 6 – Monitor | Conduct quarterly POA&M scrub; escalate 180-day items | ISSM | ISSO, PM |  | ☐ Not Started
Post-ATO / O&M | Step 6 – Monitor | Annual security review / ATO renewal preparation | ISSM | PM, ISSO, ISSE |  | ☐ Not Started
Change Control / CCB | Step 6 – Monitor | Assess security impact of proposed changes (SIAR) | ISSM | ISSO, ISSE, CCB Chair |  | ☐ Not Started
Change Control / CCB | Step 6 – Monitor | Update SSP and artifacts in eMASS for approved changes | ISSO | ISSM |  | ☐ Not Started
STATUS KEY: ☐ Not Started ¦ 🔄 In Progress ¦ ✅ Complete ¦ ⚠️ Deferred / Waived (document reason)

## RACI Matrix
RMF RACI MATRIX — Roles & Responsibilities by RMF Step
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
RMF Step / Task | AO | PM | ISSM | ISSO | ISSE | SCA | SysEng | CCB Chair | User Rep
STEP 1 – CATEGORIZE
Assign ISSM / ISSO billets | I | A | C
Define system boundary | I | C | A | R | R |  | C |  | I
FIPS 199 categorization | A | I | R | C | C |  | C |  | C
Register system in eMASS | I | I | A | R
STEP 2 – SELECT CONTROLS
Select control baseline in eMASS | C | I | A | R | C
Apply overlays / tailoring | C | I | A | R | R | C
Hold SSE / RMF kickoff meeting | I | A | R | C | C | I | C |  | I
Draft SSP outline | I | I | A | R | C
STEP 3 – IMPLEMENT CONTROLS
Integrate security into design | I | I | C | C | A |  | R
Document control implementation in SSP | I | I | C | A | R
Upload artifacts to eMASS | I | I | C | A
Open draft POA&Ms for known gaps | I | C | A | R | C
STEP 4 – ASSESS CONTROLS
Finalize SAP / lock scope | I | I | C | C | C | A
STIG / SCAP scans | I | I | C | A | C | R
Conduct TRE | I | I | C | C |  | A
Adjudicate findings / update POA&Ms | C | C | A | R | C | C
Complete SAR | I | I | C | C |  | A
STEP 5 – AUTHORIZE
Compile authorization package | I | C | A | R |  | C
PM endorsement | I | A | C
Submit package to AO | R | C | A | C
Issue ATO/IATO/DATO | A | I | C
STEP 6 – MONITOR
Establish ConMon strategy | C | I | A | R | C
Execute recurring scans | I | I | C | A
Quarterly POA&M scrub | I | C | A | R
Annual security review / ATO renewal | C | C | A | R | C | C
Security Impact Assessment (SIAR) | I | C | A | R | C |  |  | C