## ISSM
ISSM ONBOARDING — Information System Security Manager
The ISSM owns the ATO package end-to-end. Responsible for the overall RMF program for assigned systems, ensuring security posture is maintained throughout the lifecycle.
DoD 8140 Requirement: DoD 8140 IAM Level II (CISSP, CAP, CISM, or equivalent) ¦ eMASS Role: ISSM — full package authority; submit/approve workflows
Task | Description / Action | RMF Step | Timing | Complete? | Notes
eMASS System Registration | Create/claim the system in eMASS; assign all roles | Step 1 | Day 1–5 | ☐
FIPS 199 Categorization | Complete C/I/A categorization; enter in eMASS | Step 1 | Day 1–10 | ☐
Control Selection & Tailoring | Select baseline; apply overlays in eMASS | Step 2 | Week 2–3 | ☐
SSP Development Oversight | Review and approve all SSP sections | Step 2–3 | Ongoing | ☐
POA&M Management | Own POA&M register; quarterly scrub; escalate 180-day items | Step 4–6 | Quarterly | ☐
Authorization Package Assembly | Compile SSP, SAR, POA&M; submit to AO | Step 5 | Per cycle | ☐
Continuous Monitoring Oversight | Ensure scans run; review results; update eMASS | Step 6 | Monthly | ☐
Annual ATO Renewal | Initiate renewal 90 days before expiration | Step 5–6 | Annual | ☐
Change Management | Review SIARs; update SSP for approved changes | Step 6 | As needed | ☐
KEY CONTACTS — Fill in on Day 1
Authorizing Official (AO) |  |  | AO Designated Rep (AO DR)
ISSM (if filling ISSO role) |  |  | SCA / Assessor Organization
Program Manager |  |  | eMASS Help Desk | DSN or email
DAA/ISSO Peer |  |  | RMF Knowledge Service URL | rmfks.osd.mil

## ISSO
ISSO ONBOARDING — Information System Security Officer
The ISSO is the day-to-day operator of the RMF process. Directly responsible for maintaining accurate control implementation statements, artifacts, and scan results in eMASS.
DoD 8140 Requirement: DoD 8140 IAM Level I (Security+, CySA+, CAP, or equivalent) ¦ eMASS Role: ISSO — edit SSP; upload artifacts; manage POA&Ms
Task | Description / Action | RMF Step | Timing | Complete? | Notes
eMASS Access & Training | Complete DISA eMASS role-based training; get system access | All Steps | Day 1–3 | ☐
System Familiarization | Review existing SSP, boundary diagram, data flows | Step 1 | Week 1 | ☐
Control Implementation Statements | Document how each control is implemented in eMASS SSP | Step 3 | Ongoing | ☐
Artifact Upload | Upload evidence artifacts; link to controls in eMASS | Step 3–4 | Ongoing | ☐
STIG / SCAP Scan Execution | Run scans per ConMon schedule; import results to eMASS | Step 4–6 | Monthly | ☐
POA&M Entry | Enter findings with source, root cause, milestone, resource owner | Step 4–6 | Per finding | ☐
Package Support | Assist ISSM in assembling authorization package | Step 5 | Per cycle | ☐
ConMon Reporting | Track scan metrics; brief ISSM on trends | Step 6 | Monthly | ☐
KEY CONTACTS — Fill in on Day 1
Authorizing Official (AO) |  |  | AO Designated Rep (AO DR)
ISSM (if filling ISSO role) |  |  | SCA / Assessor Organization
Program Manager |  |  | eMASS Help Desk | DSN or email
DAA/ISSO Peer |  |  | RMF Knowledge Service URL | rmfks.osd.mil

## ISSE
ISSE ONBOARDING — Information System Security Engineer
The ISSE integrates security into system design and architecture. The most under-resourced RMF role. Must be engaged from concept through implementation to prevent costly late-stage rework.
DoD 8140 Requirement: DoD 8140 IASAE Level II preferred (CISSP-ISSEP or equivalent); strong systems engineering background ¦ eMASS Role: Reviewer / SME — typically read-only in eMASS; inputs to ISSO
Task | Description / Action | RMF Step | Timing | Complete? | Notes
Architecture Security Review | Analyze system design for security gaps; document findings | Step 1–2 | Per design review | ☐
Control Selection Input | Recommend tailoring decisions; identify technical controls | Step 2 | Week 2–4 | ☐
SSP Technical Sections | Author technical implementation narratives in SSP | Step 3 | Per control | ☐
Security Design Documents | Produce Security Architecture Document (SAD); data flow diagrams | Step 3 | Per milestone | ☐
STIG Applicability Review | Determine applicable STIGs for each system component | Step 4 | Pre-assessment | ☐
Scan Result Analysis | Analyze STIG/SCAP results; recommend mitigations | Step 4 | Per scan cycle | ☐
Change Impact Assessment | Assess security impact of proposed architecture changes | Step 6 | Per CCB | ☐
cATO Technical Support | Implement automated control validation for cATO pipelines | Step 6 | As applicable | ☐
KEY CONTACTS — Fill in on Day 1
Authorizing Official (AO) |  |  | AO Designated Rep (AO DR)
ISSM (if filling ISSO role) |  |  | SCA / Assessor Organization
Program Manager |  |  | eMASS Help Desk | DSN or email
DAA/ISSO Peer |  |  | RMF Knowledge Service URL | rmfks.osd.mil

## PM
PM ONBOARDING — Program Manager
The PM is accountable for the ATO as a program deliverable. Does not need eMASS technical expertise but must understand RMF timelines, resource the team adequately, and treat ATO as a gate condition on par with other milestones.
DoD 8140 Requirement: DAU Program Management coursework; no eMASS technical access required — governance role only ¦ eMASS Role: Read-only observer or no direct access; signs off on package submission
Task | Description / Action | RMF Step | Timing | Complete? | Notes
RMF Literacy Brief | Attend 2-hour RMF overview covering process, timeline, and PM obligations | All | Day 1 | ☐
ISSM / ISSO Billet Assignment | Assign qualified personnel; confirm training compliance | Step 1 | Pre-Milestone A | ☐
Resource Allocation | Budget for ISSE, SCA, and scanning tools | Step 1 | Per FYDP cycle | ☐
SSE Kickoff Participation | Attend kickoff; understand stakeholder obligations | Step 2 | Milestone A | ☐
RMF Milestone Integration | Add ATO milestones to IMS; treat as gate conditions | Step 2 | Program planning | ☐
POA&M Oversight | Review POA&M resource owners; ensure milestones are funded | Step 4–6 | Quarterly | ☐
Authorization Package Endorsement | Review and sign PM endorsement memo before AO submission | Step 5 | Per cycle | ☐
Change Control Gate | Ensure all SIARs are reviewed before CCB approval | Step 6 | Per CCB | ☐
KEY CONTACTS — Fill in on Day 1
Authorizing Official (AO) |  |  | AO Designated Rep (AO DR)
ISSM (if filling ISSO role) |  |  | SCA / Assessor Organization
Program Manager |  |  | eMASS Help Desk | DSN or email
DAA/ISSO Peer |  |  | RMF Knowledge Service URL | rmfks.osd.mil