## POA&M Tracker
Plan of Action & Milestones (POA&M) Tracker
Track every open weakness from identification through closure. Fill in new rows below the examples — do not overwrite the column headers.
POA&M ID | Weakness / Finding Name | Related Control ID | Source / Discovery Method | Weakness Description | Risk Rating | Identified Date | Scheduled Completion Date | Milestone 1 — Description | Milestone 1 — Target Date | Milestone 2 — Description | Milestone 2 — Target Date | Responsible Party / POC | Resources Required | Status | Status Date | Actual Completion Date | Days Open | Overdue? | Comments / Notes
POAM-2026-001 | Multi-factor authentication not enforced for all privileged accounts | IA-2 | Vulnerability Scan | Scan results show 6 of 14 privileged accounts can authenticate with password only; MFA is configured but not mandatory at the policy level. | High | 2026-04-02 | 2026-07-15 | Update IdP policy to require MFA for all privileged roles | 2026-05-15 | Re-scan and confirm 100% privileged-account MFA enforcement | 2026-07-10 | J. Alvarez, ISSO | IdP admin access; 4 hours of change-window time | Ongoing | 2026-06-01 |  | 67 | No | Vendor confirmed policy change is low-risk; scheduled for next maintenance window.
POAM-2026-002 | Audit logs retained for 90 days instead of the required 12 months | AU-2 | Self-Identified | SIEM storage tier was sized for 90-day retention; AU-1 policy commits to a 12-month retention period. | Moderate | 2026-03-18 | 2026-09-30 | Procure additional log-storage capacity | 2026-06-30 | Migrate historical logs and validate 12-month retention in SIEM | 2026-09-15 | T. Nguyen, System Admin | Storage budget approval; SIEM admin time | Open | 2026-06-01 |  | 82 | No | Budget request submitted 2026-05-20; awaiting approval from finance.
POAM-2026-003 | Quarterly access reviews not consistently documented | AC-2 | Internal Assessment | Two of the last four quarterly account reviews have no signed documentation on file, though informal reviews appear to have occurred. | Low | 2026-02-10 | 2026-05-01 | Stand up a documented review template and tracking log | 2026-03-01 | Complete and file Q2 2026 review using new template | 2026-04-30 | M. Okafor, ISSO | None — process change only | Completed | 2026-04-28 | 2026-04-28 | 77 | No | Closed; new review template now in use and filed in the data layer each quarter.
POAM-2026-004 | Backup restoration has not been tested in the last 12 months | CP-9 | Security Assessment | Backup jobs run nightly and complete successfully, but no test restore has been performed or documented since the last assessment cycle. | Moderate | 2026-05-05 | 2026-08-01 | Schedule and execute a full test restore in the staging environment | 2026-07-01 | Document results and update the Contingency Plan with findings | 2026-07-25 | T. Nguyen, System Admin | Staging environment access; 1 day of downtime in staging | Open | 2026-06-01 |  | 34 | No
POAM-2026-005 | Legacy TLS 1.0 fallback still enabled on the public-facing interface | SC-7 | Vulnerability Scan | External scan flagged that the load balancer still accepts TLS 1.0/1.1 connections as a fallback for a small number of legacy client integrations. | Critical | 2026-05-22 | 2026-06-20 | Identify and notify the remaining legacy clients of the cutover date | 2026-06-05 | Disable TLS 1.0/1.1 and confirm via external re-scan | 2026-06-18 | J. Alvarez, ISSO | Coordination with 2 external partner contacts; change-control approval | Ongoing | 2026-06-01 |  | 17 | No | Risk-accepted on an interim basis by the AO through 2026-06-20 only; documented in risk register.
No
No
No
No
No
No
No
No
No
No
No
No
No
No
No
No
No
No
No
No
No
No
No
No
No
Formulas:
Days Open = IF([Status]="Completed",[Actual Completion Date]-[Identified Date],TODAY()-[Identified Date])
Days Open = IF([Status]="Completed",[Actual Completion Date]-[Identified Date],IF([Identified Date]="","",TODAY()-[Identified Date]))
Overdue? = IF(AND([Status]<>"Completed",TODAY()>[Scheduled Completion Date]),"Yes","No")
Overdue? = IF(AND([Status]<>"Completed",[Status]<>"",[Scheduled Completion Date]<>"",TODAY()>[Scheduled Completion Date]),"Yes","No")

## Summary Dashboard
POA&M Summary Dashboard
All figures below recalculate automatically from the POA&M Tracker sheet.
By Status |  | By Risk Rating
Status | Count | Risk Rating | Count
Open | 2 | Critical | 1
Ongoing | 2 | High | 1
Completed | 1 | Moderate | 2
Delayed | 0 | Low | 1
Risk Accepted | 0
Total tracked items | 5
Overdue Items
Overdue? | Count
Yes — past scheduled completion date | 0
No — on track or closed | 30

## Field Guide
POA&M Tracker — Field Guide
What each column means and how to fill it in.
Column | How to fill it in
POA&M ID | A unique tracking number for the weakness, e.g. POAM-YYYY-### . Keep numbering sequential within the year so items are easy to reference in conversation and in eMASS.
Weakness / Finding Name | A short, specific name for the weakness — specific enough that someone scanning the list knows what it is without opening the row.
Related Control ID | The NIST SP 800-53 control ID this weakness maps to, e.g. AC-2 or SC-7. Use the Control Implementation Statement Library to cross-reference what "right" looks like for that control.
Source / Discovery Method | How the weakness was found: Vulnerability Scan, Security Assessment, Internal Assessment, Audit, Self-Identified, or Incident.
Weakness Description | Plain-language description of the actual gap — specific enough that a new ISSO inheriting this system understands the issue without asking.
Risk Rating | Low, Moderate, High, or Critical. Pick this from the dropdown — it drives the color coding and the dashboard counts.
Identified Date | The date the weakness was first identified (yyyy-mm-dd). This is the anchor date for the Days Open calculation.
Scheduled Completion Date | The date remediation is planned to be complete. This is the anchor date for the Overdue flag — keep it realistic, not aspirational.
Milestone 1 / Milestone 2 — Description & Target Date | Break remediation into concrete, checkable steps with their own target dates. Add more milestone column pairs if a weakness needs more than two.
Responsible Party / POC | The specific person accountable for closing this item — name and role, not just a team name.
Resources Required | What it will actually take to close this — budget, tools, access, staff time, vendor coordination.
Status | Open, Ongoing, Completed, Delayed, or Risk Accepted. Pick this from the dropdown — it drives the color coding and the dashboard counts.
Status Date | The date the Status value was last reviewed or changed. Update this every time you touch the row, even if the status itself didn't change.
Actual Completion Date | Filled in only when Status = Completed. Leave blank until the item actually closes — this date drives the final Days Open calculation.
Days Open (auto-calculated) | Calculated automatically: Actual Completion minus Identified Date if closed, or Today minus Identified Date if still open. Don't type into this column.
Overdue? (auto-calculated) | Calculated automatically: shows "Yes" when an item is not yet Completed and today's date is past the Scheduled Completion Date. Don't type into this column.
Comments / Notes | Anything a future reader needs to know — interim risk acceptances, blockers, vendor responses, links to evidence in the data layer.
Working tips
• Update Status Date every time you touch a row — a stale status is one of the first things assessors flag.
• Never delete a closed item. Move it down or filter it out — your closure history is evidence of a working program.
• Keep the Risk Rating honest. Inflated or deflated ratings undermine trust in the whole POA&M when an assessor spot-checks them.
• Cross-reference the Related Control ID against the Control Implementation Statement Library to write a tighter, more specific Weakness Description.
• Re-run the Summary Dashboard before any review meeting — it recalculates instantly and gives you talking points without manual counting.