PROPOSAL TO THE AUTHORIZING OFFICIAL

# RMF COMMANDER Product Requirements Document

AI-Assisted RMF Portfolio Visibility and Compliance Support Platform

| Field | Value |
| --- | --- |
| Document Type | RMF COMMANDER Product Requirements Document |
| Version | 1.0 - Updated Standalone Document |
| Date | 22 May 2026 |
| Prepared By | LEO CHRISTIE, NH-III, Information System Security Manager |
| Organization | Air Force Services Center, VTOS / Cybersecurity Division, JBSA-Lackland, Texas 78236 |
| Submitted To | FRANCISCO SALGUERO, SES, NAFI Authorizing Official, USAF HAF AF/A1X |
| Classification | UNCLASSIFIED // FOR OFFICIAL USE ONLY |
| AI RMF Alignment | NIST AI RMF 1.0 - GOVERN, MAP, MEASURE, MANAGE functions |

# 1. Product Vision

RMF COMMANDER is an AI-assisted mobile and web platform that gives authorized RMF personnel secure portfolio visibility, smart compliance alerts, AI-supported documentation drafting, natural-language RMF queries, and executive briefing support. The system extends visibility and drafting support without replacing eMASS or the exercise of judgment in authorization.

# 2. Target Users

| Role | Primary Use Case | Key Features |
| --- | --- | --- |
| ISSM | Portfolio management, ATO oversight, POA&M ownership. | Dashboard, alerts, documentation assistant, briefing generator. |
| ISSO | System-level controls, continuous monitoring, POA&M updates. | Documentation assistant, alerts, and NL query. |
| AO Representative | Portfolio-level risk review and package tracking. | Dashboard, briefing generator, and monthly status reports. |
| SCA | Assessment coordination and evidence review. | Controls view and documentation review outputs. |
| Program Manager | High-level posture visibility and leadership reporting. | Dashboard and briefing generator. |

# 3. MVP Functional Requirements

| ID | Feature | Priority | Requirement |
| --- | --- | --- | --- |
| FR-01 | Portfolio Dashboard | MVP | Display ATO status, expiration countdown, POA&M severity counts, control posture, scan freshness, and categorization for assigned systems. |
| FR-02 | Smart Alert Engine | MVP | Notify role-scoped users of 90/60/30-day ATO windows, POA&M slips, and workflow state changes. |
| FR-03 | AI Documentation Assistant | Phase 2 | Generate draft control statements, POA&M language, and monitoring summaries with source citations and human review. |
| FR-04 | Vulnerability Triage | Phase 3 | Map ACAS/Tenable findings to controls and POA&Ms and suggest draft remediation language. |
| FR-05 | Natural Language Query | Phase 2 | Answer portfolio questions using authorized data only. Include source citations for every answer. |
| FR-06 | Executive Briefing Generator | Phase 3 | Generate AO, PM, and leadership posture summaries in mobile card, PDF, and PPTX-ready formats. |

# 4. Non-Functional Requirements

| Area | Requirement |
| --- | --- |
| Data classification | IL4 handling in a DoW-authorized cloud boundary. No classified data in pilot. |
| Authentication | CAC/PIV-derived credential via Purebred on MDM-enrolled devices. |
| Session management | 15-minute JWT and full wipe after 5 minutes backgrounded or logout. |
| Data at rest | No eMASS data persisted on the client device. Session memory only. |
| Transport | TLS 1.3 minimum and mTLS for backend-to-eMASS. |
| AI boundary | No IL4 data transmitted outside the DoW cloud boundary for AI processing. |
| Audit logging | All API calls, AI prompts, outputs, and approvals logged with 1-year minimum retention. |
| STIG compliance | DISA Mobile App STIG review before operational deployment. |

# 5. Roadmap

| Phase | Timeline | Deliverables | Gate Criteria |
| --- | --- | --- | --- |
| Phase 1 | Days 1-90 | Pilot kickoff, stakeholder validation, test/sandbox access, dashboard MVP, alert engine. | ATO expiration alerts functional on test dataset. |
| Phase 2 | Days 45-120 | Backend infrastructure, authentication service, API proxy, secrets management, logging/SIEM integration. | Backend deployed in DoW cloud and role-scoped access validated. |
| Phase 3 | Days 90-150 | Mobile app, ACAS integration, vulnerability triage, and session security controls. | App deployed to MDM test devices and STIG checks underway. |
| Phase 4 | Days 120-180 | AI layer, RAG pipeline, documentation assistant, NL query, briefing generator. | Drafts include citations and require human approval. |
| Phase 5 | Days 150-240 | STIG remediation, control assessment, penetration test, authorization package assembly, ATO submission. | Full package submitted to HRM AO via eMASS. |

# 6. Acceptance Criteria

A pilot user can view full mock portfolio posture in less than five minutes.

Configured 90/60/30-day ATO alerts to fire with 100 percent accuracy in test.

AI-generated drafts are labeled AI-drafted, source-cited, and blocked from use until human approval.

No production eMASS data is used during the pilot.

No client device persists in the authorization package content.

AO receives 30-day touchpoint briefings and final go/no-go report.

Point of Contact:

LEO CHRISTIE

NH-III, Information System Security Manager

Air Force Services Center, VTOS

JBSA-Lackland, Texas 78236

Commercial: [Phone Number]

DSN: [DSN Number]

Email: [Email Address]

# 7. Compliance Check: RMF Commander — AI-Assisted RMF Platform (Pilot Deployment)

Initiative: Deploy RMF Commander as an AI-assisted mobile and web platform for authorized DoD/Air Force RMF personnel. The platform provides read-only portfolio visibility into eMASS data (ATO timelines, POA&M, control posture), AI-assisted documentation drafting with a human-approval gate, and executive briefing support. Data processed: CUI/IL4 RMF portfolio content. Hosted in Azure Government IL4. Users authenticate via CAC/PIV. Pilot uses sandbox/test eMASS data only.

## Summary

Proceed with conditions. Several compliance gates must be formally completed before the pilot can expand beyond sandbox data, and the AI layer introduces specific obligations under the emerging DoD AI governance policy that require documented review prior to operational deployment. No showstoppers are present for the sandbox pilot itself. Production use requires that gates 1 through 9 be cleared, as documented in the requirements package.

## Applicable Regulations and Policies

| Regulation / Policy | Relevance | Key Requirements |
| --- | --- | --- |
| FISMA (44 U.S.C. § 3551 et seq.) | RMF Commander is a federal information system processing CUI; FISMA compliance is mandatory | Complete RMF process: categorize, select controls, implement, assess, authorize, monitor |
| DoDI 8510.01 — DoD RMF | DoD-specific implementation of FISMA governs the authorization process for this system | Register in eMASS, complete SCTM, obtain IATT, then ATO from the designated AO |
| NIST SP 800-53 Rev 5 | Baseline control framework for the security plan | MODERATE baseline minimum; document inherited controls from Azure Gov; assess residual controls |
| DISA Cloud Computing SRG v1r3 | Governs use of commercial cloud for DoD workloads; IL4 designation required for CUI | Use DISA PA-authorized Azure Government services only; enforce IL4 data boundary |
| DISA STIGs | Technical hardening requirements for all components | Web App, Mobile App, Azure Foundation, Container Platform, App Security, and Development STIGs applicable |
| Privacy Act of 1974 (5 U.S.C. § 552a) | RMF portfolio data includes PII (names, roles, contact info of system owners, ISSOs, AOs) | Publish or identify applicable SORN; limit collection to authorized purposes; no disclosure without consent or exception |
| DoDD 5400.11 / DoDI 5400.11 | DoD Privacy Program governs PII handling within DoD systems | Complete Privacy Impact Assessment (PIA); apply Fair Information Practice Principles |
| EO 14110 / DoD AI Adoption Strategy | Governs use of AI in federal/DoD systems; requires risk management and human oversight documentation | Complete AI Impact Assessment; document human-in-the-loop controls; align to NIST AI RMF 1.0 GOVERN/MAP/MEASURE/MANAGE functions |
| NIST AI RMF 1.0 | Voluntary but aligned with DoD AI Adoption Strategy and documented as a PRD reference | Document AI risk profile; establish governance structure; measure bias/reliability of RAG outputs; define management/response procedures |
| DoDI 8582.01 | Privacy in the DoD applies to systems that collect or use PII | System Privacy Plan (SPP) required as part of ATO package; privacy controls from NIST SP 800-53 Privacy appendix |
| DISA MO (Mobile Operations) | Governs mobile app deployment on DoD networks and MDM-enrolled devices | MDM enrollment required; DISA Mobile App STIG review; Purebred/PKI auth required |
| DoD Zero Trust Strategy (2022) | Governs identity, access, and device trust for DoD systems | CAC/PIV with MFA, device health validation, least-privilege role scoping, session controls |

## Requirements

| # | Requirement | Status | Action Needed |
| --- | --- | --- | --- |
| 1 | Register RMF Commander as a system in eMASS | Not Met | Submit new system registration to the MAJCOM eMASS admin. This is Gate 2 — nothing downstream proceeds without it. |
| 2 | System categorization (FIPS 199 / CNSSI 1253) | Not Met | Categorize at MODERATE (expected given CUI/IL4 content). Document in eMASS. |
| 3 | SCTM at MODERATE baseline documented | Not Met | Build SCTM. Document inherited controls from Azure Gov IL4 PA. Identify system-specific controls for assessment. |
| 4 | Privacy Impact Assessment (PIA) completed | Not Met | PIA is required before operational use. Identify all PII collected (user roles, names, contact details in portfolio records). |
| 5 | System Privacy Plan (SPP) included in ATO package | Not Met | Required per DoDI 8582.01. Aligns with NIST SP 800-53 privacy control families (AP, AR, DI, DM, IP, SE, TR, UL). |
| 6 | SORN identified or published | Unknown | Determine whether the existing AFSVC SORN covers RMF portfolio data or whether a new/amended SORN is needed. |
| 7 | AI Impact Assessment documented | Not Met | Required before the AI layer goes operational. Document model type, training data provenance, RAG grounding sources, human-approval gate design, bias/reliability testing approach. |
| 8 | NIST AI RMF alignment documented (GOVERN/MAP/MEASURE/MANAGE) | Partial | PRD references NIST AI RMF 1.0. A formal alignment document (AI risk profile) must be produced for the ATO package. |
| 9 | IATT obtained from AO | Not Met | Required before testing with real (non-sandbox) eMASS data. Submit after SCTM is drafted and STIG reviews are underway. |
| 10 | Azure Government IL4 tenant confirmed | Unknown | Verify existing AFSVC Azure Gov tenant authorization level or provision a new one. Confirm IL4 service list for planned components (APIM, Key Vault, App Service, Sentinel). |
| 11 | Azure Key Vault is used for all secrets; no credentials in code | Met (design) | Architectural requirements are documented and enforced. Verify in code review before production deployment. |
| 12 | TLS 1.3 minimum for client-to-backend; mTLS for backend-to-eMASS | Met (design) | Documented in PRD NFRs. Must be verified in implementation and STIG review. |
| 13 | No IL4 data transmitted outside the DoW cloud boundary for AI processing | Met (design) | Documented as a hard constraint. Must be verified in the architecture review and pen test. |
| 14 | 15-minute session timeout; 5-minute background wipe | Met (prototype) | Implemented in prototype (session timer now live). Must be enforced at the backend JWT layer, not only in the UI. |
| 15 | No eMASS data persisted on the client device | Met (design) | Documented NFR. Must be verified in DISA Mobile App STIG review. |
| 16 | All API calls, AI prompts, outputs, and approvals are logged with 1-year retention | Not Met | Logging/SIEM infrastructure not yet deployed. Azure Sentinel or authorized Splunk is required. |
| 17 | STIG compliance documentation for all components | Not Met | STIGs must be run and their findings documented before the ATO package is submitted. Open the CAT I findings block submission. |
| 18 | Penetration test by DISA-approved tester or AF red team | Not Met | Required before ATO package submission. |
| 19 | Pilot limited to sandbox/test eMASS data | Met | eMASS API Justification Memo correctly scopes the request to the sandbox only. Do not mix sandbox and production credentials. |
| 20 | Production eMASS API access requires separate AO approval | Met (documented) | Correctly stated in the memo and requirements package. Must be enforced as a process gate, not merely documented. |

## Risk Areas

| Risk | Severity | Mitigation |
| --- | --- | --- |
| AI-generated content is accepted into RMF artifacts without adequate human review | High | Human-approval gate enforced in UI. Must also be enforced in audit logs — every approval event must record the reviewer’s identity, timestamp, and the specific draft content approved. |
| RAG grounding sources become stale or inaccurate | Medium | Document the grounding corpus (NIST SP 800-53 r5, CNSSI 1253, eMASS dataset snapshot). Establish a refresh cadence. Stale grounding could produce draft language inconsistent with current control baselines. |
| Sandbox eMASS credentials inadvertently used against the production endpoint | High | Enforce environment separation at the Key Vault level — separate vaults or separate secrets for sandbox vs. production. The backend proxy must validate the endpoint URI against an allowlist. |
| PIA/SORN gap — PII in RMF portfolio data not formally assessed | Medium | RMF records contain names, roles, and contact information of personnel. This is PII under the Privacy Act. A PIA is required before operational use regardless of classification level. |
| AI Impact Assessment not completed before the AI layer goes live | High | Under current DoD AI governance guidance, deploying an AI system without a documented impact assessment constitutes unauthorized AI use. Complete and file before the AI layer is enabled in any non-sandbox environment. |
| Session wipe is enforced only in UI, not in the backend | High | The 15-minute JWT expiry and 5-minute background wipe must be enforced server-side. A UI-only countdown can be bypassed by replaying a valid token. Backend token validation must unconditionally reject expired tokens. |
| Azure Gov service components not on DISA IL4 APL | Medium | Not every Azure Government service holds a current DISA PA at IL4. Verify each planned component (APIM, Key Vault, App Service, Container Apps, Sentinel) against the current DISA Cloud Computing SRG Appendix/APL before build. |
| STIG CAT I findings discovered late in the process | Medium | Begin STIG checklists in parallel with build, not after. Late discovery of CAT I findings can delay ATO submission by months. |

## Recommended Actions

Register the RMF Commander in eMASS immediately. This is the critical path item — the SCTM, PIA, SPP, and IATT requests all require an active eMASS system record.

Submit the eMASS API Justification Memo to your MAJCOM eMASS administrator and request sandbox credentials in parallel with the eMASS registration.

Complete the Privacy Impact Assessment before the AI layer or any non-sandbox data is processed. Identify the applicable SORN or initiate a new one with your Privacy Officer.

Produce the AI Impact Assessment document. At minimum: describe the model, grounding sources, human-approval gate design, and what happens when the system is uncertain. File this with the ATO package.

Stand up logging infrastructure (Azure Sentinel or authorized equivalent) before the backend handles any real data. Audit log completeness is a FISMA and DoDI 8510.01 requirement, not optional polish.

Begin STIG checklists now, in parallel with build. Run Web App and Azure Foundation STIGs first; they will surface the most findings.

Confirm the Azure Government IL4 tenant and verify each planned service against the current DISA Cloud Computing SRG Appendix before committing to a technology stack.

## Approvals Needed

| Approver | Why | Status |
| --- | --- | --- |
| FRANCISCO SALGUERO, SES — NAFI Authorizing Official | ATO authorization decision and IATT approval | Pending — leadership review package submitted |
| MAJCOM eMASS Administrator | System registration and sandbox API credential provisioning | Pending — memo drafted |
| AFSVC Privacy Officer | PIA review and SORN determination | Not initiated |
| AFSVC Legal / JAG | AI Impact Assessment and Privacy Act compliance review | Not initiated |
| DISA or AF Red Team | Penetration test (required for ATO package) | Not initiated — Gate 7 |

## Further Review Recommended

AI governance: The DoD AI Adoption Strategy and applicable DAF/AFSVC AI governance policy should be reviewed by your JAG or legal advisor before the AI layer goes into any operational (non-sandbox) use. The human-in-the-loop design is strong, but a formal legal review of the AI Impact Assessment will be required for the ATO package in most MAJCOM authorization processes.

Privacy Act and SORN: Your Privacy Officer and JAG should make the SORN determination. Whether an existing AFSVC system-of-records notice covers RMF portfolio data (which includes personnel names and roles) is a legal question that requires review of the current SORN inventory — not a determination that can be made in this assessment.

eMASS API access scope: The memo correctly limits the request to sandbox credentials. Before any production eMASS API access is requested, legal should review the scope of data that would be accessible and confirm that it is covered by the system’s authorization boundary and any applicable data-sharing agreements between AFSVC and the eMASS program office.